## 20.03.2020
"Gas Transmission System Operator of Ukraine" LLC scheduled maintenance works plan. Complexes influencing Russian gas transit in 2020.
| Works complexes | Duration | Gas delivery/acceptance capacities at MS | Remarks
02.06 - 05.06
| Maintenace of ATI pipeline at CS Orlovka-2 | 96 | Guaranteed gas transmission at MS: Uzhgorod=110,8 mcm/day, Drozdovychy=12,5 mcm/day, Beregovo=28,6 mcm/day, Orlovka=11,5 mcm/day. Guaranteed gas transmission at MS: Suja (P=75) Q=150,7 mcm/day, Sokhranovka (P=75) Q=27,4 mcm/day
11.08 - 14.08
| Maintenance at EKKR pipeline, CS Zinkiv EKKR pipeline stop to conduct repair of valve 101 DN1400 at the connection of CS Zinkiv (+ valve repair at CS Reshetylivka) | 96 | Guaranteed gas transmission at MS: Uzhgorod=110,8 mcm/day, Drozdovychy=12,5 mcm/day, Beregovo=28,6 mcm/day, Orlovka=11,5 mcm/day. Guaranteed gas transmission at MS: Suja (P=75) Q=150,7 mcm/day, Sokhranovka (P=75) Q=27,4 mcm/day | EKKR pipeline stop for 1 day
05.10 - 09.10
| Maintenace at UPU and "Progress" pipelines at CS Romny, DN150 valves replacement | 120 | Guaranteed gas transmission at MS: Uzhgorod=125,0 mcm/day, Drozdovychy=11,9 mcm/day, Beregovo=33,5 mcm/day, Oleksiivka=1,8 mcm/day, Grebenyky=10,92 mcm/day Guaranteed gas transmission at MS: Suja (P=75) Q=155,22 mcm/day, Sokhranovka (P=75) Q=27,4 mcm/day
26.10 - 28.10
| Maintenance of Komarno - Drozdovychy pipeline, CS Komarno | 72 | Maximum transmission at MS Drozdovychy Q=11,9 mcm/day; gas offtake stop at MS Hermanovice
Pipeline repair works
| 1. UPU pipeline repair and replacement of interconnector-valve between UPU and "Progress" pipelines |  | Works will not be conducted in 2020
| 2. Reconnection of constructed section of "Soyuz" pipeline (1633 km, CS Mashivka - CS Kremenchug section) | starting from 12 October (14 days) | Guaranteed gas transmission at MS: Uzhgorod=125,0 mcm/day, Drozdovychy=11,9 mcm/day, Beregovo=33,5 mcm/day, Oleksiivka=1,8 mcm/day, Grebenyky=10,92 mcm/day Guaranteed gas transmission at MS: Suja (P=75) Q=155,22 mcm/day, Sokhranovka (P=75) Q=27,4 mcm/day | "Soyuz" pipeline 1616,94 km - 1644.63 km section disconnection
| 3. Re-insulation of EKKR pipeline, 382,84 km - 383,77 km section, Sumy subdivision | April - June | Works will be performed in accordance with the GTS operation mode | CS Romny inlet pressure 66,5 kg/cm2
| 4. Rozdilna - Izmail DN800 pipeline major overhaul and insulation coating replacement of 296,6 km - 302,64 km and 328,1 km - 335,0 km sections. | February 24 - December 31 | Guaranteed capacity at points: Kaushany (UA-MD direction) - 3,96 mcm/day, Isaccea (gas ofttake from Romania) - 3,96 mcm/day
| 5. Maintenance at "Komarno - Drozdovychy" DN500 pipeline. 9,7 km - 44,9 km section disconnection. | June - October | "Komarno - State border" DN700 trunk pipeline will be operational Guaranteed transmission at MS Drozdovychy = 12,5 mcm/day (IV quarter - 11,9 mcm/day)
| 6. DUD-2 DN1400 pipeline; 185,8 km. Connection of constructed cleaning pig receiving camera and pipeline section reinstalling | 288 hours (from June 02) | Section from valve №220 (177,27 km) to state border (187,2 km) removal from operation
| 7. DUD-2 DN1400 pipeline; 176,25 km. Connection os straightened section of metering point connection to DUD-2 pipeline | 01 - 22 September | Section from valve №30A (175,45 km) to valve №220 (177,27 km) removal from operation | Interruption of transmission at MS Budince
| 8. Removal of flaws by installation of metallic reinforcing couplings in pressure conditions of 0,7 P(operational) at UPU, "Progress", "Soyuz", EKKR, ATI, SHDKRI and RI pipelines. | during the year
Works with stop of UPU, "Progress", "Soyuz" pipelines and other works, scheduled for 2020 and not included in "Maintenance plan" will be performed in accordance with the Ukrainian GTS operation mode.
** - during works with "Soyuz" pipeline stop at CS Mashivka - CS Kremenchug section, gas flows reallocation between MS Sokhranovka and MS Suja is possible