## Англійськи сайт
"Gas Transmission System Operator of Ukraine" LLC Maintenance Schedule for 2021
№ | Maintenace complex name | Terms |  | Duration, hours | Technical capacity January-December 2021 (mcm/day)
Physical capacity in January-December 2021, accounting the limitations during maintenance (mcm/day)
[5 empty] | Suja | Sokhranivka | Orlovka |  | V.Kapusany | Budince |  | VIP Bereg |  | GCP GAZ-SYSTEM/ UA TSO
|  | Start | End |  | entry | entry | exit | entry | exit | exit | entry | exit | entry | exit | entry
[5 empty] | 87 | 37.6 | 20 | 11.5 |  | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
1 | Maintenance at "ATI" and "UPU" pipelines (CS Stavyshche, CS Golyatyn) | 2021-04-13 | 2021-04-15 | 72 | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
2 | Maintenance at "EKKR" pipeline (CS Reshetylivka) | 2021-04-20 | 2021-04-22 | 72 | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
3 | Maintenance at "UPU" and "Progress" pipelines (CS Grebinka, CS Stavyshche "Progress") | 2021-05-11 | 2021-05-13 | 72 | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
4 | Maintenance at "Sojuz" pipeline (CS Gusyatyn) | 2021-05-17 | 2021-05-21 | 120 | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
5 | Maintenance at "UPU" and "Progress" pipelines (CS Sofiivka, CS Illintsi, CS Gusyatyn (120 hours), CS Golyatyn "Progress") Launch capera valve №80 DN1400 replacement. Disconnection of "Progress" section: 3761,63 km – 3762,642 km (connection point of CS-34B Sofiivka) | 2021-05-25 | 2021-05-27 | 72 (120) | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
6 | Maintenance at "Sojuz" pipeline (CS Novopkov (96 hours)), "KAB" pipeline (CS Kirovogradska) and "SHDKRI" pipeline (CS-1 Orlovka) | 2021-06-08 | 2021-06-10 | 72 (96) | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
7 | Maintenance at "EKK" pipeline (CS Glushkivska) and DUD-2 pipeline (CS Uzhgorod-2 (120 hours)) | 2021-06-15 | 2021-06-17 | 72 (120) | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
8 | Performance of maintenance works with full stop of CS Uzhgorod | 2021-06-21 | 2021-06-25 | 120 | 87 | 37.6 | 20 | 11.5 | 125 | 0 | 0 | 72.7 | 19.5 | 12.9 | 0
9 | Maintenance at "Sojuz" pipeline (CS Borova, CS Mashivka, CS Oleksandrivka, CS Gaysyn, CS Khust) | 2021-06-22 | 2021-06-24 | 72 | 87 | 37.6 | 20 | 11.5 | 125 | 0 | 0 | 72.7 | 19.5 | 12.9 | 0
10 | Maintenance at "EKK" pipeline (CS Grebinka (96 hours)), "ATI" pipeline (CS-2 Orlovka) and DUD-2 pipeline (CS Uzhgorod-1) | 2021-07-06 | 2021-07-08 | 72 (96) | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
11 | Maintenance at "Sojuz" pipeline (CS Pervomayska (96 hours), CS Kremechuk, CS Talne, CS Bar, CS Bogorodchany | 2021-08-03 | 2021-08-05 | 72 (96) | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
12 | Valve replacement of the connector between "UPU" and "Progress" pipelines №3812,6(П) Dn1200 and "zero" valve of branch-pipeline to GDS Sakhnivka Disconnection of "UPU" section: 3643.8 km - 3690.2 km; 0 km - 23.8 km (backup line) and "Progress" section 3812.2 km - 3835.16 km | 2021-08-09 | 2021-08-26 | 408 | 72 | 37.6 | 20 | 11.5 | 66.5 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
13 | Maintenance at "UPU" and "Progress" pipelines (CS Bar and CS Bogorodchany) | 2021-08-09 | 2021-08-18 | 240 | 72 | 37.6 | 20 | 11.5 | 66.5 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
14 | Maintenance at "Komarno-Drozdovychy" pipeline (CS Komarno) and DUD-2 pipeline (CS-3 Dolyna) | 2021-08-10 | 2021-08-12 | 72 | 72 | 37.6 | 20 | 11.5 | 66.5 | 24 | 42.5 | 72.7 | 19.5 | 10 | 0
15 | "UPU" pipeline repair together with linear valves №3667, №3667,7, №70У1, №70У2 DN1200 repacement. Disconnection of "UPU" sections: 3643.8 km - 3690.2 km; 0 km - 23.8 km (backup line) | 2021-08-27 | 2021-09-07 | 288 | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
16 | Maintenance at "UPU" and "Progress" pipelines (CS-32 and CS-32П Romny) | 2021-09-13 | 2021-09-17 | 120 | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
17 | Maintenance at "EKKR" pipeline (CS-3 Romny) | 2021-09-20 | 2021-09-24 | 120 | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
18 | Maintenance at "Rozdilna - Izmail" pipeline sections: 296.6 km - 302.64 km; 328.1 km - 335.0 km (In case of unfinished works by the end of 2020) | January | February | 1416 | 87 | 37.6 | 20 | 4 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0
19 | Reinsulation together with particular pipes replacement at 9.379 km - 29.873 km, 29.9 km – 44.5 km of "Komarno - Drozdovychy" Dn500 | January | December | 8760 | 87 | 37.6 | 20 | 11.5 | 125 | 24 | 42.5 | 72.7 | 19.5 | 12.9 | 0