## Обмеження
"Gas Transmission System Operator of Ukraine" LLC Maintenance Schedule for 2022, influencing transmission capacities or pressures
№ | Name | Remarks | Dates |  | Duration, hours | Technical capacity from January to December 2022 (mcm/day)
Technical capacity from January to December 2022, accounting the limitations during maintenance (mcm/day)
[6 empty] | Sujah | Sokhranivka | Orlovka/Isaccea |  | V.Kapusany | Budince |  | Beregovo/Beregdaroc |  | Drozdovychy/Hermanovice
|  |  | Start | End |  | entry | entry | exit | entry | exit | exit | entry | exit | entry | exit | entry
[6 empty] | 87 | 37.6 | 20 | 11.5 |  | 24 | 42.5 | 48.8 | 19.5 | 12.9 | 0
1 | "Komarno-Drozdovychy" DN500 pipeline repair (9,3 - 29,9 km) |  | January | June |  | 87 | 37.6 |  | 11.5 | 125 |  | 42.5 | 26 | 19.5 | 12.9
2 | SHDK pipeline repair (406,203 - 416,197 km). Pipe section and coating replacement. | Disconnection of CS Yagotyn - CS Boyarka section. | March | December |  | No influence on transit. Gas pressure increase in SHPK, SHDK and EDK pipelines at CS Dykanka and CS Lubny - CS Yagotyn sections during gas offtake from production.
3 | 3667 km at "UPU" pipeline; 3812 km at "Progress" pipeline. Dnipro river crossing. "UPU" pipeline repairs with the replacement of valves № 3667, № 3667,7, № 70У1, № 70У2 Ду1200, switch-valve between "UPU" and "Progress" № 3812,6(П) Ду1200 and "0" valve of branch pipeline to GDS Sakhnivka. | Disconnected sections of pipelines. "UPU": 3643,8 km - 3690,2 km; 0 km - 23,8 km (reserve line) "Progress": 3812,2 km - 3835,16 km Simultaneous disconnection of "UPU" and "Progress" for 6 days. (from 09 August 2022). Then "Progress" in operation. | 2022-08-09 | 2022-08-26 | 17 days | 69 | 37.6 |  | 11.5 | 61,7 (63,6 from 16.08 to 18.08) |  | 42.5 | 26 | 19.5 | 12,9 (11,0 from 16.08 to 18.08)
4 | Maintenance at "Komarno-Drozdovychy" pipeline (CS Komarno). |  | 2022-08-16 | 2022-08-18 | 72 | 69 | 37.6 |  | 11.5 | 63.6 |  | 42.5 | 26 | 19.5 | 11
5 | Maintenance at SHPK-SHDK-EDK pipeline (CS Dykanka). | Replacement of valve № 2 unit № 2. Replacement of valves № 4 unit №№ 1-7. | 2022-10-03 | 2022-10-07 | 120 | No influence on transit. Gas pressure icnrease in SHPK, SHDK and EDK pipelines at CS Dykanka entry during gas offtake from production.
6 | Maintenance at SHPK-SHDK-EDK pipeline (CS Lubny). | Replacement of ball valve № 8Е DN700 of connection node. Replacement of valve № 17Б DN400 of connection node. | 2022-10-17 | 2022-10-21 | 120 | No influence on transit. Gas pressure icnrease in SHPK, SHDK and EDK pipelines at CS Lubny entry and CS Dykanka exit during gas offtake from production.